## Overview
Overview — Five-Module WBS
Module Area | Modules | Sub-Modules | Features | Completion %
1. YourVault | 8 | 19 | 84 | 78.95%
2. Knowledge Pack | 8 | 16 | 63 | 78.12%
3. Side Panel (Intent Outputs) | 6 | 10 | 44 | 80%
4. Workflows - Super Admin | 6 | 10 | 42 | 52%
5. Workflows - Chat (Tenant) | 8 | 16 | 66 | 81.25%
Grand Total | 36 | 71 | 299 | 75.63%
STATUS LEGEND
Complete | Fully implemented with no TODOs (100%)
In Progress | Partially implemented or has TODOs / placeholders (50%)
Planned | Surface scaffolded but not built (10%)
Phase 2/3 | Backlog only — depends on backend or future sprint (0%)

## 1. YourVault
1. YourVault
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | Vault landing & hero | Hero + scope tabs | - 'Ask across your documents' hero with sparkle gold-bordered NL search bar - ⌘K keyboard shortcut to focus the search input - Org-Admin scope tabs above hero (All / Org-wide / Mine) - Upload + New Document buttons top-right of hero - Folder name + breadcrumb display when inside a folder | Complete | Per Aashna 2026-04-27 redesign. Hero stays static; only breadcrumb swaps when navigating into a folder.
|  | Step-numbered toolbar | - 1. Visualize — List / Grid toggle (visual only in v1) - 2. {N} docs context counter - 3. Refine — collapses Date / Uploader / Type / Sort chips behind a dropdown - 4. Move — 'Drag a doc into chat' hint - Chips render only when openFilterMenu === 'refine' | Complete | Refine chip overflow added 2026-04-27 to reduce visual noise.
2.0 | Folder structure | Nested folders | - Folders can contain sub-folders to arbitrary depth (v1 ships 2-level mocks) - Left rail folder list with click-to-navigate - Folder rows: name + doc-count badge - MATTERS-only left-rail framing (2026-05-11 PM call dropped user-folders block) - Cross-matter filter pills under search bar - Breadcrumb above hero when inside a folder | Complete | Folder state in 'yourai_document_vault_folders_v1' localStorage via documentVaultStore.
|  | Folder operations | - Create folder via modal (name + parentId) - Rename folder via kebab - Delete folder (deletes contained docs after confirm) - Move docs between folders (drag or kebab → Move) - Recursive upload — drag a folder, all contents go to active folder | Complete | Wendy P3 / P4 / P5 — nested + recursive + UI label cleanup.
3.0 | Document table | Root view columns | - Folder → Name → Owner → Size → Modified → Actions - Folder column bolded as primary case-file identifier - Sort by column header click (Name / Modified) - Inside-folder view drops the Folder column | Complete | Ryan Robertson framing — 'folder' reads as the matter for an attorney's brain.
|  | Per-row actions | - Kebab menu: Open, Download, Rename, Move, Delete - Click row → opens document detail (right rail — deferred) - 'Use in chat' button when picker is open - Drag row → attach to chat | In Progress | Inspect right-rail panel from designer mockup deferred; click-to-open currently does nothing in root view.
4.0 | Search & filter (P8) | Ask-anything NL parser | - Top search bar with sparkle icon - NL parsing: 'find indemnification across Acme contracts' → set filters + run search - AI-set transient filters (resultLimit / askExplanation / sort) drop on user-typed query - Explicit chip filters (date / uploader / type) persist across typing - 'All documents' tree click also drops transient filters | Complete | P8 v1 — Option 2 shipped 2026-04-27.
|  | Filter chips | - Date chip — Last 7d / 30d / This year / All - Uploader chip — pick from active org users - Type chip — PDF / DOCX / XLSX / TXT - Sort chip — Newest / Oldest / Name asc / Name desc - Clear all link when any chip is active | Complete | Chips collapse behind 'Refine' dropdown to keep toolbar compact.
|  | Content-aware search | - Search hits both filename and extracted `content` field - Highlight matched terms in result row preview - Empty-state when zero matches: 'No documents match "X"' | Complete | Substring search over name + description + content; case-insensitive.
5.0 | Upload & creation | Upload pipeline | - Single-file upload via Upload button - Drag-and-drop into page (folder-aware) - Real text extraction via extractFileText helper (PDF / DOCX / TXT) - Per-file processing status (uploading → extracting → ready) - Failed extraction → 'Flagged for Review' status | Complete | Shared src/lib/file-parser.ts pipeline used by chat attach + KP + workflow Pre-Run.
|  | New Document modal | - Field order: Folder → Document name → Description → File - Folder dropdown defaults to current folder context - Description field optional - File picker accepts PDF / DOCX / TXT (≤25 MB) - Save creates the vault entry + extracts content + closes | Complete | Field order changed 2026-04-29 per Ryan Robertson.
|  | Sample seed docs | - 4 real PDFs in public/sample-docs/ (NDA, Sample Case Brief, MSA, Compliance Memo) - Each entry carries extracted `content` so bot can actually read them - Storage key bumped to yourai_document_vault_v2 - Seed PDFs generated by /tmp/gen-sample-pdfs.py (fpdf2) | Complete | Re-run gen-sample-pdfs.py if sample text in sampleVaultContent.ts changes.
6.0 | Chat integration | Vault picker modal | - Triggered from chat '+' button OR from SearchScopePill YourVault option - Search input + filtered doc list + folder breadcrumbs - 'Use in chat' CTA per row + 'Open YourVault →' footer link - Detach row when an active vault doc is already pinned - Closing without picking keeps prior scope | Complete | Mirrors KP picker modal pattern; both use same search-first layout.
|  | Scope-as-conversation-context | - Selected vault doc inlined into messageForEdge under [Documents attached to this conversation] - Per-doc cap 5,000 chars in the system prompt - Source pill 'Answered from: <doc name>' on grounded responses | Complete | Scope commits only when the user actually picks a doc inside the modal.
7.0 | Permissions & visibility | Role-based scope | - External User → only their own docs / docs shared into their workspace - Internal / Manager → org-wide + their own - Org Admin → everything - Mine vs Org-wide flag per doc | Complete | Filter lives inside DocumentVaultPanel based on currentRole.
|  | Sharing & promotion | - Promote 'Mine' doc to 'Org-wide' via kebab - Confirmation prompt before promoting - Visibility filter re-evaluated after promote - Audit-log entry on every promote (planned) | In Progress | Promote path works; audit-log entry needs the audit pipeline to be wired.
8.0 | Backend-pending (Sprint 2+) | Metadata enrichment (P8.3) | - Page count via best-effort PDF parse - lastModifiedAt stamp - Auto-stamp workspaceId on workspace-attached docs - Enables 'files over 200 pages' / 'files in Acme matter' queries | Phase 2/3 | Wendy P8.3 — backend-dependent. Without metadata, certain NL queries can't return useful results.
|  | Content semantic search (P8.4) | - pgvector ingestion pipeline - Hybrid retrieval (dense + BM25 + RRF + rerank) - Per-file token math (chunking, overlap, dedup) - Async ingestion on upload - ~3-week effort per .claude-context/vault-content-rag-plan.md | Phase 2/3 | Wendy P8.4 — the real grounding engine. Today's substring search is a stopgap.
|  | Large-file strategy (P12) | - Auto-chunking for 500-page PDFs (family-law app-close exports) - Per-case MD summary index - Possible open-source memory system per Hog | Phase 2/3 | Wendy P12 — backend-dependent.

## 2. Knowledge Pack
2. Knowledge Pack
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | Pack catalog (landing page) | Card-grid layout | - Vertical pack cards (post-2026-04-27 Aashna redesign — flipped from horizontal) - Hero with 'Knowledge Packs' title + Create New Pack button - Filter tabs: All / Org-wide / Mine - Search bar (filters by pack name + description) - Per-card doc count + link count + scope badge | Complete | Same full-page chrome as Vault / Workspaces / Workflows.
|  | Pack actions per card | - Click card → opens Edit modal - Kebab: Rename / Duplicate / Delete / Share toggle - Active-pack indicator (gold pill) when pack is currently attached to chat | Complete | Active-pack state lives on ChatView, lifted through props.
2.0 | Pack lifecycle (create / edit / delete) | EditKnowledgePackModal | - Pack name (required) + description (optional) - Scope toggle: Mine / Org-wide - Add documents tab — file picker (PDF / DOCX / TXT) - Add links tab — URL + label (metadata-only in v1) - Per-doc preview row with size + extracted-content status - Save / Cancel buttons (Save = green when valid) | Complete | Single modal handles both Create and Edit flows via existing-pack-id prop.
|  | Document extraction | - runDocExtraction() calls extractFileText (same parser as chat attach) - Real PDF / DOCX / TXT parsing on upload - Status flow: uploading → extracting → ready - Per-doc cap 5,000 chars when inlined into chat - Strips File ref before save; persists name / size / uploaded / content | Complete | Replaced 2026-05-06 simulateDocPipeline stub with real extraction; v1→v2 storage bump forced re-seed.
|  | Pack deletion | - Delete confirmation modal - Disable delete when pack is currently active in chat - Toast confirmation post-delete | Complete
3.0 | Seed packs | Bundled defaults | - Hartwell NDA Template Pack — NDA template + risk checklist + redline - M&A Diligence Pack — checklist + Meridian precedent + indemnification clauses - California Labor Law Pack — CA Labor Code summary + § 16600 / Edwards rule - Privacy Pack — GDPR + CCPA reference - All carry real extracted `content` from src/data/samplePackContent.ts | Complete | Seeded via seedPacksIfEmpty(DEFAULT_KNOWLEDGE_PACKS) on first mount.
4.0 | Pack picker (chat integration) | Modal picker | - Triggered from Pack pill in chat input row - Search input (sticky when > 5 packs) - Filtered pack list with 'Use' CTA per row - 'No pack' row at top to clear active pack - 'Manage knowledge packs →' footer link | Complete | Mirrors YourVault doc-picker modal for consistency.
|  | Pack pill in chat input | - Shows active pack name when one is attached - '⌘ Knowledge pack' label when no pack active - Click opens picker modal - Gold styling when active (matches 'Using {pack} pack' status line) | Complete | Pack pill is independent of Intent and SearchScope pills.
5.0 | Grounding & chat prompt injection | Edge prompt payload | - Active pack content prepended to messageForEdge under [Knowledge Pack reference for this conversation] - Per-doc cap 5,000 chars (truncated with notice) - Pack content sent alongside attached doc content (both inlined) - Source pill 'Answered from Pack: {pack name}' rendered when pack-grounded | Complete | Edge route (api/chat.ts) is where the inline happens — client fallback (callLLM) does NOT do this.
|  | Intent orthogonality | - Changing intent never changes active pack - Changing pack never changes active intent - Independent session-level states (per Conventions doc) | Complete | By design — attorney can pair any intent with any pack.
6.0 | Permissions & sharing | Visibility filter | - Mine packs visible to owner only - Org-wide packs visible to every member of the org - External User → no pack picker (KP feature gated off externals) | Complete | isExternalUser check inside Sidebar gates the Knowledge packs nav item.
|  | Share / promote toggle | - Toggle in EditKnowledgePackModal: Mine ↔ Org-wide - Confirmation prompt when promoting (irreversible without an admin) - Visibility re-evaluates immediately | In Progress | UI exists; visibility filter logic should be re-verified once a second user account is in localStorage (per 2026-05-06 session note).
7.0 | Persistence | localStorage store | - Key: yourai_knowledge_packs_v2 - Mirrors documentVaultStore pattern (loadPacks / savePacks / seedPacksIfEmpty) - v2 bump 2026-05-07 forced re-seed after content-field fix - Save on every mutation via useEffect | Complete | src/lib/knowledgePackStore.ts.
8.0 | Backend-pending (Sprint 2+) | Link fetching pipeline | - Save link with URL + title + extracted body - CORS + sanitization layer for arbitrary URLs - Re-fetch on link rot (broken link badge) - Inline link content into chat prompt (like doc content) | Phase 2/3 | Links save metadata-only today; no grounding. Sprint-2 lift due to CORS + link-rot complexity.
|  | Server-side pack dedup | - Detect duplicate doc content across packs - Suggest 'use existing doc from Pack X' on upload - Reduce token cost when multiple packs share a template | Phase 2/3 | Backend-dependent.
|  | Pack analytics | - Which packs are most often attached to chat - Which docs in a pack get cited most - Per-attorney pack usage in Usage & Costs panel | Phase 2/3 | Requires audit log + cost telemetry.

## 3. Side Panel (Intent Outputs)
3. Side Panel (Intent Outputs)
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | Inline preview chip | Chat-thread chip | - Eyebrow line (intent name uppercase — RISK MEMO / SUMMARY / etc) - DM Serif title (matter / document / 'N findings') - 'Open' pill when panel is closed; 'Viewing' pill when open and showing this artifact - Click → opens panel anchored to this message - Per-intent accent color on the chip border | Complete | Replaces inline IntentCard render (which was blowing out the chat flow).
2.0 | Right-rail panel layout | Docked panel | - 540 px width sibling of chat-main (chat shrinks; NOT an overlay) - White background (flipped from warm cream 2026-05-04) - Auto-opens on first card-intent arrival - Anchored to message ID via activeArtifactMsgId - Header: Copy as Markdown / Fullscreen / Close buttons | Complete | Sibling-panel pattern same as MyTimePanel / AuditLogsPanel.
|  | Fullscreen mode | - Centered ~720 px column - Same header controls (Copy / Exit fullscreen / Close) - Exit fullscreen returns to docked mode - Body remains scrollable | Complete
|  | Markdown body | - ReactMarkdown rendering with 720 px column - h1 + meta line + h2 sections + bullets + plain blockquotes - DM Sans body, DM Serif only for h1, h2 with subtle border-bottom - No pills / tiles / coloured rails — pure report layout | Complete | PM call: 'should look like a report, not fancy shit.'
3.0 | Card → markdown serializers | Per-intent converters | - src/lib/cardToMarkdown.ts — 7 serializers (Summary, Comparison, CaseBrief, Research, RiskMemo, ClauseAnalysis, Timeline) - Each serializer turns structured card JSON into clean markdown - pickTitle() heuristic — rejects 'Risk Assessment of Uploaded Documents' / 'Untitled case' / 'Legal Inquiry' - Generic-title regex auto-falls-back to documentName (extension stripped) - Centralised so adding a new intent = add a serializer; panel picks it up automatically | Complete | Timeline serializer remains but Timeline intent itself was retired.
|  | Empty-state branch | - Per-card detection (schema-shaped envelope w/ no real data) - Empty-state card variant renders in panel instead of grids of '—' - Upload prompt + sibling-intent hint inside the empty state - find_document keeps inline FileResultsCard — does NOT use the panel | Complete | Detection rule: all schema-required string fields blank + no documentName + empty arrays. See .claude-context/card-empty-state-pattern.md.
4.0 | State management | Panel state | - activeArtifactMsgId on ChatView — anchors the panel to a specific bot message - Opens automatically on new card-intent arrival - Switching demos (/demo-risk → /demo-summary) updates panel content - Close button → setActiveArtifactMsgId(null) - Click chip after close → re-opens panel to that artifact | Complete
5.0 | Copy + share | Copy-as-Markdown | - Copy button in panel header - Writes plain markdown text to clipboard - Tooltip reads 'Copy as Markdown' - Toast confirmation post-copy | Complete | Tooltip text fixed 2026-05-04 — was incorrectly reading 'Copy as JSON'.
|  | Share / export | - PDF export of the report - Share-as-link (URL with artifact ID) - Citation linking back to attached doc passages - Print-stylesheet for browser print | Phase 2/3 | Browser print works today as a stopgap. Real share-as-link needs backend persistence.
6.0 | Backend-pending | Server-side artifact persistence | - Save generated artifacts to a backend store - Re-open a prior artifact via thread history - Versioning (regenerated artifacts keep history) - Cross-device sync | Phase 2/3 | Today artifacts live only in chat-thread state; lost on refresh of an old thread.

## 4. Workflows - Super Admin
4. Workflows - Super Admin
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | Templates list (SA portal) | Table view | - List of all workflow templates across all tenants - Columns: Name / Practice Area / Step Count / Last Edited / Status / Actions - Search by template name or description - Filter by practice area + status (Active / Draft / Archived) - Create New Template button top-right | Complete | Lives at /super-admin/workflows. Backed by mockData; switch to real API once dev team ships.
2.0 | Template editor | Step builder | - Centered hero with step-pill indicator - White rounded panel body - Navy step-number circles per step - Drag-to-reorder steps - Add / remove / duplicate step - Uppercase mono section labels | Complete | Picker + Builder rewritten 2026-04-25 from Aashna's chat-mode mockups.
|  | Per-step config | - Operation type dropdown (Risk / Summary / Comparison / Case Brief / Research / Clause Analysis) - System prompt textarea (per-step override) - Output type (card / markdown / table) - Reference doc per step — warm-beige inset, vault picker - Optional skip flag (conditional execution) | Complete | Prompts default to workflowPrompts.ts operation library.
|  | Save & validation | - Save Draft / Publish buttons - Required-field validation per step - Test run inline (executes against a sample doc) - Auto-save on field blur | In Progress | Test-run inline is mocked; needs real execution wiring same as chat workflows.
3.0 | Operation library | Base operations | - 6 base ops — Risk Assessment, Document Summarization, Clause Comparison, Case Brief, Legal Research, Clause Analysis - v2-tightened prompts (word targets + citation hedging + table syntax + findings-vs-actions distinctness) - All defined in workflowPrompts.ts - Anti-hallucination string: 'Not covered by supplied documents.' (literal, every operation prompt) | Complete | v2 tightening 2026-04-24, blind pass.
|  | Custom operations | - Define a new op from scratch (name + system prompt + output schema) - Promote a per-step prompt back into the global library - Versioning per op | Planned | Today ops are hard-coded in workflowPrompts.ts; making them editable requires backend storage.
4.0 | Distribution | Tenant visibility | - Active / Inactive flag per template - Per-tenant override (push to a specific firm) - Default-all-tenants behavior on publish - Audit row on every distribution event | In Progress | Distribution is mocked end-to-end; backend pipeline needed.
5.0 | Audit & versioning | Edit history | - Last edited by / when displayed on each template - Full version history viewer (diff per step) - Rollback to a prior version - Approve / reject changes (multi-admin flow) | Planned | Single-line 'Last edited' shown today; full history viewer is backend-dependent.
6.0 | Backend-pending | Real distribution pipeline | - Push template changes to live tenant chats without redeploy - Tenant-level enable/disable for in-flight runs - Versioned rollout (canary 10% → 50% → 100%) | Phase 2/3 | Backend-dependent.
|  | Usage analytics per template | - Run count per template (today / 7d / 30d) - Average duration per step - Failure rate per step + per template - Surface in SA Reports & Analytics | Phase 2/3 | Telemetry pipeline needed.

## 5. Workflows - Chat (Tenant)
5. Workflows - Chat (Tenant)
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | Workflow picker | Unified grid | - Single unified grid (no maxWidth cap) - AI PIPELINES eyebrow row - Per-card: practice-area top stripe + name + short description - StatTiles per card (runs in last 7d / avg duration / success rate) - Running-in pill when a run from that template is active - PIPELINE op-icon row at card bottom (per-step operation icons) | Complete | Rewritten 2026-04-25 from Aashna's chat-mode mockups. The earlier auto-fit + maxWidth 960 cap was retired same day.
|  | Filter & search | - Underline filter tabs (All / Recent / Favourites) - Search by template name + description - Click card → opens Pre-Run modal (if doc-required) or runs directly | Complete | Favourites are localStorage-only.
2.0 | Pre-Run modal | Document gathering | - Multi-file upload - Drag-and-drop into modal - Per-file processing status (extracting / ready / failed) - classifyDocs() auto-classification on upload-ready - Per-row uppercase type chip (Contract / Brief / Discovery / Pleading) - Summary banner ('3 contracts, 2 briefs') above doc list | Complete | Classification wired into PreRunModal 2026-04-24 afternoon.
|  | Run kickoff | - Run button enabled when min-doc-count satisfied - AlreadyRunningAlert guard if another run is active - Closes modal + auto-opens WorkflowRunPanel | Complete | One-run-at-a-time guard prevents concurrent runs.
3.0 | Workflow Builder (tenant) | Step editor | - Centered hero + step-pill indicator - Add / remove / reorder steps - Per-step: operation pick + system prompt edit + reference-doc picker - Save Draft / Save & Run - In-panel CTAs at bottom | Complete | Tenant builder mirrors SA editor with reduced permissions (no template publishing).
4.0 | Run execution | workflowRunner (singleton) | - Module-level singleton with subscribe / notify - subscribeRun(runId, cb) — components watch one run by id - Survives component unmount + panel swap (artifact panel pattern) - getActiveRunId() / getRun(id) / listRuns() exports | Complete | src/lib/workflowRunner.ts. Same pattern as sessionTimer (AI-time meter).
|  | workflowExecutor | - Per-step LLM call via /api/chat (Edge function) - Step N receives summary of steps 1..N-1 (prior-step chaining) - Per-step prompt assembly: operation system prompt + user instruction + prior outputs (capped ~3500 chars each) + uploaded docs (capped ~8000 chars each) + reference doc + workspace context - Streams response via ReadableStream - 90s timeout per step via AbortController - Failure on step → run status 'failed' + error string per step | Complete | src/lib/workflowExecutor.ts. The prior-step chaining is the whole point — Generate Report synthesizes prior outputs, not raw docs.
|  | Run states | - queued → running (currentStepIndex 0..N-1) → complete ¦ failed ¦ cancelled - Cancellation: in-flight AbortController fires - Per-step timing stored on the run object | Complete
5.0 | Run Panel UI | WorkflowRunPanel | - Multi-run list (active + recent) - Per-run row: template name + status + currentStep / total - Click row → expands to step-by-step status - Cancel button when running - Re-run button when complete / failed | Complete | Sibling panel of chat-main.
|  | WorkflowProgressCard (in-thread) | - Appears in chat thread when a run is triggered from chat - Pulsing dot + step name + 'View progress →' link - Updates on subscribeRun ticks - Collapses to summary line on complete | Complete | scrollToRunningPanel() scrolls the chat to the in-thread card on demand.
6.0 | Report card | WorkflowReportCard (Option D) | - Document-style report layout (h1 + meta + per-step sections) - Per-step output rendered in the section's body - Final synthesis step as the Conclusion - Renders inside the chat thread below the progress card - Citation badges per finding | Complete | Option D shipped 2026-04-24. Embedded in chat thread, not in IntentArtifactPanel.
|  | Export from report | - Copy as Markdown - Print (browser stylesheet) - Download PDF | In Progress | Copy as Markdown works; PDF export is browser-print stopgap.
7.0 | Persistence & history | localStorage runs | - Key: yourai_workflow_runs_v1 - Stores last ~50 runs - Survives refresh + reopens to last-active run on demand | Complete
|  | Run history view | - Filter by template / status / date range - Reopen any past run's report card - Bulk delete / archive | In Progress | List exists; filter + reopen wiring needs polish.
8.0 | Backend-pending | Server-side run store | - Move runs out of localStorage into a real backend - Cross-device sync (start on laptop, view on phone) - Per-attorney run history surfaces in Reports & Analytics - Real-time collaboration on a single run | Phase 2/3 | localStorage is fine for v1 but doesn't scale beyond a single browser.
|  | Cost telemetry per run | - Token cost per step - Total run cost - Aggregate per template in Usage & Costs | Phase 2/3