## Overview
YourAI — Work Breakdown Structure (Overview)
Platform / Module Area | Total Modules | Total Sub-Modules | Total Features | Completion %
Tenant Chat | 10 | 40 | 283 | 97.75%
Super Admin | 8 | 17 | 99 | 75.29%
Org Admin | 11 | 15 | 89 | 88%
Shared & Infra | 6 | 13 | 79 | 66.15%
GRAND TOTAL | 35 | 85 | 550 | 86.71%
Status legend
Complete | Fully implemented with no TODOs (Completion% weight = 100%)
In Progress | Partially implemented or has TODOs / placeholders (50%)
Planned | Surface scaffolded but not built (10%)
Phase 2/3 | Mentioned in plan / backlog only (0%)

## Tenant Chat
Tenant Chat
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | Authentication & Onboarding | Login | - Email + password entry form - Password visibility toggle (eye icon) - OTP verification step (6-digit input with auto-focus chaining) - "Forgot Password" link - OTP resend with 30-second cooldown timer - Demo credentials display panel (hidden by default) - Redirect parameter support (?redirect=/chat/...) with same-origin validation - Role-based redirect (External → /chat/workspaces, others → /chat/home) | Complete | Real API calls via AuthContext; localStorage-backed session; OTP hardcoded as mock
|  | Sign Up | - Email + password entry - Password confirmation field - Email verification check - Invited-user fast path (?invited=1&email=...&firm=...) — pre-verified, locks email + firm name, skips OTP/survey/payment - Link to login page | Complete | Invited-user path lands directly on /chat/home with viaInvite:true on profile
|  | Forgot Password | - Email entry field - "Send Reset Link" button - Success messaging | Complete | Mock; no real email delivery
|  | Reset Password | - Password reset token handling (from email link) - New password + confirm password entry - "Reset Password" submit button | Complete
|  | Onboarding (Plan → Payment) | - Two-step active flow: Plan selection → Payment - Plan tiers: Free, Professional, Team, Enterprise - Stripe-style payment form (mock) - Skip-survey path (Wendy P1 fix — survey removed from active flow) - Profile fields (role, primary state, firm size, practice areas) deferred to a post-onboarding nudge - Progress indicator + Back/Next navigation - "Complete Onboarding" final submit | Complete | Cut to two steps 2026-04-27 (Wendy P1). renderStep1..4 still defined for future profile nudge.
2.0 | Chat Interface | Main Chat Surface | - Message bubbles (user right-aligned navy, bot left-aligned white) - Streaming response rendering via ReadableStream - Markdown support (bold, italic, lists, code blocks) - Source badges: "Document" / "Knowledge Base" / "Workspace" / "Vault" - Timestamp display per message - Message copy + per-message action menu - Trailing decoder flush so multibyte UTF-8 doesn't lose bytes at chunk boundary - Real Edge errors surfaced verbatim (no silent fallback masking) | Complete | Real /api/chat streaming; client-fallback callLLM is dead in prod (2026-04-25).
|  | Empty State (Ryan's spec) | - Hero: gold sparkle eyebrow + DM Serif H1 + caption - Big primary chat input directly under hero - Drop-files tile under input (auto-hides once pendingAttachments.length > 0) - Merged icon-pill row: General Chat → Review/Summarise/Draft → Legal Research → Case Law Analysis → More operations ▾ - Source dropdown (General Chat / Workspace ▸ / YourVault ▸) replaces + attach button - Knowledge Pack dropdown alongside - Input placeholder: "Ask anything about your documents or Alaska law…" - Trust footer with privacy disclaimer - padding-top: 12vh anchor (post Aashna polish) - <900px viewport caps merged-pill row at 4 visible (rest in More overflow) - <768px viewport stacks input row vertically | Complete | Aashna P1 polish promoted from /chatviewv2 preview to /chat 2026-04-29. Capability-grid attempt was reverted same-day.
|  | Intent Selector & Auto-Switch | - 13 intents in registry (general_chat + 12 specific) - Empty-state pill row + populated-chat collapsed dropdown - Auto-switch from general_chat on first message via keyword matcher - "Switched to X mode" system note when auto-switching - Suggestion banners: single-match + tied multi-pick variant, 600ms debounce - Cross-intent sticky threshold (≥2-point keyword gap to exit specific intent) - legal_qa suppressed unless in general_chat - hasManualIntentPick flag gates auto-switch paths to respect user picks - Mid-thread intent switch is seamless (no 'start fresh' interrupt) | Complete | detectIntent + detectAllIntents in src/lib/intentDetector.ts. Manual-pick override fix landed 2026-04-29.
|  | Input & Controls | - Expandable textarea (auto-height up to 140px) - Programmatic pre-fill auto-grow via useEffect on input value - Send button (disabled while streaming) - Demo slash commands (/demo-summary /demo-comparison etc.) - Paste support - Stop/cancel via AbortController | Complete | Pre-fill auto-grow fix 2026-04-29: setInput() doesn't fire onInput so a useEffect runs auto-resize.
|  | Sidebar Search (Chat history) | - Search Chats input at top of sidebar - Case-insensitive match across title OR preview OR any message body - Italic 80-char snippet preview centred on match (when matched on body) - Source order: messages (active thread) → threadMessagesRef → seed THREAD_MESSAGES | Complete | Extended in place 2026-04-29 (no new surface).
|  | Tile-based Home (/chat/home) | - Login default for non-externals; externals still go to /chat/workspaces - 6 role-aware tiles: General Chat, Workspaces, YourVault, Workflows, Knowledge Packs, Invite Team - Hero: gold sparkle eyebrow + DM Serif H1 ("Hi {name}, what would you like to do?") - Tile chrome: page surface #F4F5F7, 1.5px #DCE0E6 border, etched static box-shadow - Hover lifts shadow depth (no border-colour swap) - Each tile sets the matching panel's show-flag and navigates | Complete | HomeTileLauncher lives inside ChatView when initialView==='home'.
3.0 | Intent Response Cards | Summary Card | - Editorial shell with gold accent - Header: Document Summarisation eyebrow + document name + clauses/size/date - Executive summary paragraph - Metadata 2×2 grid (Parties, Key Dates, Governing Law, Key Obligations) - Key Points enumerated bullets (max 8) - Optional 'Needs attention' gold-border callout - Empty-state shell: 'No document supplied' + upload hint + sibling-intent suggestion | Complete | Intent: document_summarisation. Forces response_format: json_object.
|  | Comparison Card | - Editorial shell with navy accent - Side-by-side or pipe-delimited table (subject vs reference) - Delta column: Added / Removed / Modified / Favorable / Unfavorable - Per-cell ≤25 words - Empty-state shell: 'No documents supplied' + upload prompt | Complete | Intent: clause_comparison.
|  | Case Brief Card | - Editorial shell with green accent - Header: Case Law Analysis eyebrow + case name + court/year - Sections: Facts / Holding / Reasoning / Implications / Application - Empty-state shell with sibling-intent hint | Complete | Intent: case_law_analysis.
|  | Research Brief Card | - Editorial shell with indigo accent - Header: topic + jurisdiction + stats block (statute/case/principle counts) - Standard sections: Applicable Statutes / Relevant Case Law / Key Principles / Practical Implications - 'Verified' vs 'Principle-only' (confidence-tagged) split - Citations array per section - Empty-state shell: 'Need a more specific question' + worked example query | Complete | Intent: legal_research. KB-backed; doc not required.
|  | Risk Memo Card | - Editorial shell with red accent - Header: matterName + documentName + risk count - Findings grid (severity high/medium/low pills, location, optional verbatim quote, owner, recommendation) - Optional 'Top Takeaway' blockquote (gold left border) - Recommended Actions section (distinct from findings) - Array.isArray guards on findings + flags - Empty-state shell: 'No document supplied' + upload prompt | Complete | Intent: risk_assessment.
|  | Clause Analysis Card | - Editorial shell with orange accent - Priority-ordered clause list (HIGH first, max 15) - Per-clause: title, location, risk, optional quote, interpretation, optional recommendation - Array.isArray guard on clauses - Empty-state shell: 'No document supplied' + upload prompt | Complete | Intent: clause_analysis.
|  | Timeline Card | - Editorial shell with green accent - Chronological event list (earliest first) - Per-event: date, kind (event/deadline/milestone/filing), label, optional description, optional source ref - Date-string format preserved from source - Array.isArray guard on events - Empty-state shell: 'No dated events found' + sibling hint | Complete | Intent: timeline_extraction.
|  | File Results Card (Find Document) | - Client-only intent — no Edge round-trip - Trigger-word stripping (find / search / where is / show me / list, anchored on file/doc/document) - Trailing-phrase handling ('from my document vault' etc.) - Variant-aware render: empty vault / empty query / no match / 1 / 2-5 / top 5 of N - Per-row Use button dispatches yourai:vault-use-doc → vault doc attaches to thread - Folder-path search match | Complete | Intent: find_document. Substring filter over name + description + fileName + folder breadcrumb (NOT content).
4.0 | Document Attachment & YourVault | Document Upload (in-chat) | - + button opens Attach Menu (now Source dropdown post-Ryan-spec) - Drag-drop zone overlay (when dragging files over chat) - Multi-file support (up to 5 per chat; beyond = limit-reached message) - File-type validation (PDF, DOCX, XLSX, TXT, PNG, JPG) - Per-file text extraction via extractFileText() - Upload progress indicator + filename display - 'Document N (added HH:MM): filename' label in system prompt - Additive uploads (DEC-095 retired): new docs APPEND to sessionDocContext - Inline thread note: 'New documents added. Start fresh →' window event - Doc content stitched into /api/chat message body under '[Documents attached…]' header | Complete | Edge sees only body.message + history + intent — content MUST be inlined client-side.
|  | YourVault Panel — Folder Tree | - Full-page two-pane Finder layout (left rail + main) - Left rail (280px fixed): LIBRARY eyebrow → 'All documents' pinned → FOLDERS eyebrow → recursive tree - Chevron expand/collapse, 16px depth indent, navy-tinted active row - Auto-expands ancestors of active folder - Sticky '+ New folder' footer - Nested folders via VaultFolder.parentId - Default seed: Contracts › Acme Corp › MSA & Schedules - Deleting a folder re-parents children to the deleted folder's parent (no orphans) | Complete | Wendy P3/P4/P5 — Aashna full-page redesign 2026-04-27.
|  | YourVault Panel — Documents Table | - Hero: VAULT eyebrow + DM Serif H1 (current folder name) + parent breadcrumb caption - Sticky 56px toolbar: Search/Ask-anything bar + filter chips - Root view 6 cols: Folder → Name → Owner → Size → Modified → Actions (Folder is primary identifier) - Inside-folder 5 cols: Name → Owner → Size → Modified → Actions - Folder cell bolded (DM Sans 14 px / weight 600 / navy), click jumps to folder - Owner pills, 'from chat' badges, row-hover kebab menu (Edit / Delete / Share-org-wide) - Empty state: 56px circular icon + serif headline + Upload folder / + Document CTAs | Complete | Column reorder 2026-04-29 per Ryan Robertson 'case file' framing.
|  | YourVault — Search & Ask-Anything | - Toolbar search input is dual-purpose Search OR Ask-anything bar (gold sparkle) - Plain typing → live substring filter on name + description + fileName (NOT content) - Enter / 'Ask ✨' button → LLM-backed NL parser via /api/chat (JSON-only schema) - Parser returns: search, dateFilter, uploaderId, fileType, sortBy, limit, explanation - Gold callout shows model's one-sentence interpretation - Filter chips: Date · Uploaded by · Type · Sort (sticky — explicit user choice) - Transient filters (resultLimit / askExplanation / sortBy) clear on user typing or All-documents click - 'Top N' badge surfaces when parser sets a limit - Empty state: 'No documents found.' | Complete | P8.1 + P8.2 shipped 2026-04-27. Content semantic search (P8.4) backlog.
|  | YourVault — Recursive Folder Upload | - 'Upload folder' button uses webkitdirectory - Walks each File.webkitRelativePath, recreates the directory tree - Dedupes by name+parent so re-uploads merge - Toast: 'Uploaded N files with folder structure preserved.' | Complete | Wendy P4 shipped 2026-04-27.
|  | YourVault — Document Modals | - New Document modal field order: Folder → Document name → Description → File - Depth-indented folder dropdown (↳ Acme Corp under Contracts) - Edit Document modal with same fields - Delete confirmation - Move to Folder dialog - Sample seed: 4 real PDFs in public/sample-docs/ with content stamped on entries | Complete | Modal field order updated 2026-04-29.
|  | Knowledge Packs Panel | - Full-page two-pane redesign (Aashna 2026-04-27) - Card grid (packs are destinations, not files) - PackRow vertical layout: header (icon + title + ownership pill + kebab) → 2-line description → footer (counts + share-org-wide toggle + Use) - Owner facet moved to toolbar dropdown chip (Owner: All ▾) - Pinned scopes (All / Org-wide / Mine) in segmented control - Create / Edit / Delete via modal: name, description (300-char limit), visibility radio, docs section, links section - Active pack indicator + click-to-activate - Per-user star to favorite - Empty state: 'No packs found.' | Complete | yourai_knowledge_packs_v1; favorites in yourai_workflow_favourites_v1 (shared key).
5.0 | Workflows (Multi-Step AI Pipelines) | Workflows Picker | - AI PIPELINES gold eyebrow + DM Serif title + 'Running in: Global / Main Site' navy pill - StatTiles: Featured / Your Library / Running / Recent (uppercase mono label, 22px navy value) - Underline-active tabs with count chips - Rounded-pill search box - Single unified grid: repeat(auto-fill, minmax(340px, 1fr)) — no maxWidth cap - Card: 3px practice-area top stripe, 32×32 icon tile, eyebrow, Platform pill, ownership pill, Clock·N steps·~Xs pill - PIPELINE op-icon row (28×28 tiles + → arrows + +N more overflow) - 2-line description clamp - 'Updated X / Run →' footer link - Star toggle per card (per-user favorites) - "← Dashboard" breadcrumb | Complete | 2026-04-25 redesign from Aashna chat-mode mockups.
|  | Workflow Builder (2-step wizard) | - Top bar: ← Workflows breadcrumb + outlined Cancel only - Centered hero on warm-lilac gradient: title, context-aware subtitle, two-step pill indicator - Centered 720px white rounded panel body - Section labels: uppercase mono WORKFLOW DETAILS / WORKFLOW STEPS - Details: name (gold * + counter), practice area, status segmented pill (Active/Draft, org-admin only), description (N/300), visibility radio cards - Steps: navy-filled numbered circle, drag handle (when >1 step), op pill with ~Xs · description - Step name input + Document type instructions input (each w/ helper + counter) - Advanced options pill (navy when expanded) - Reference-doc panel — warm-beige inset with navy-filled tabs - Footer: Add Step (left) · N/8 steps (centre) · Estimated total ~Xs (right) - Primary CTAs in panel footer (not top bar) - Delete workflow confirmation dialog | Complete | Max 8 steps. Full rewrite 2026-04-25 from 8 Aashna mockups.
|  | Pre-Run Modal | - Header row: workflow name + practice-area chip + steps/duration - Knowledge source banner (blue in workspace, neutral in main chat) - Yellow sibling warning when workspace has no docs - Upload dropzone (drag + click, file-type filter display) - Per-row uppercase type chip from classifyDocs() (NDA / CONTRACT / LEASE / MEMO / etc.) - Summary banner: 'Identifying…' → 'Identified: 2 contracts, 1 memo' - Run enabled once at least one upload is Ready - Cancel button - Classification advisory only — never blocks Run | Complete | Stage 1 of FRD_Incorrect_Document_Handling.docx. classifyDocs returns [] on failure.
|  | Workflow Execution & Run Panel | - Each step POSTs to /api/chat with full messages[] payload (op system prompt + assembled user message) - Prior-step chaining — step N receives structured summary of steps 1..N−1 - Per-step output capped at ~3500 chars; uploaded docs ~8000 chars; reference docs ~6000 chars - ReadableStream consumption with 90s timeout via AbortController - 480px right-docked flat-white panel with 3px accent left border + 3px progress ruler - WorkflowProgressCard variant='embedded' inside RunRow (single-card render) - Per-run row: workflow name + practice-area pill + step bars + status (Running/Done/Error/Skipped) - Estimated time remaining + Cancel during run + Expand/collapse - Per-step output preview with 'Read more' expand - Fullscreen toggle (880px centred column) - Multiple concurrent runs allowed; sidebar running-strip is the minimized state | Complete | workflowRunner singleton survives unmount; runs persist in yourai_workflow_runs_v1.
|  | Workflow Report Card (Option D) | - Document-style render — no outer border, no accent stripe, 760px centred column - Eyebrow: WORKFLOW REPORT · practice area · date - DM Serif 30px title - Meta caption: knowledge source · doc count · optional partial-failure note · runtime - Executive Summary (DM Serif headings, DM Sans body, gold-rail blockquotes) - Generated <relative> footer + View audit log (ghost) + Download PDF (outlined navy) - Audit log modal: per-step markdown output (collapsible) + Documents analysed pills + Retry for failed steps - Download PDF opens a clean printable HTML window (browser native Save-as-PDF) | Complete | Option D 2026-04-24. WorkflowReportCard component.
|  | Workflow Operations (6 system prompts) | - read_documents — classify + structure each upload (type, parties, dates, structure) - analyse_clauses — clause-by-clause breakdown (priority-ordered HIGH first, max 15, short quote when phrase drives risk) - compare_against_standard — pipe-syntax table, ≤25 words/cell, 5-value Delta whitelist - research_precedents — jurisdiction + statutes + case law, hedge-over-fabricate, two-format (Verified vs Principle-only) - compliance_check — 11-framework whitelist (SOC 2/HIPAA/GDPR/CCPA/GxP/FCPA/PCI-DSS/SOX/NIST/ISO 27001/user-stated) - generate_report — synthesis (not re-analysis) of prior step outputs; findings vs actions distinct - Shared rules: 'Not covered by supplied documents.' literal vague-doc protocol - Per-operation word targets (250 / 400-700 / 300-500) - Concrete citation format [Doc: filename, §X] - Blockquote for top takeaway | Complete | v2 tightening 2026-04-24. src/lib/workflowPrompts.ts. Adding a new op = update prompts + OPERATION_CONFIG + OP_ICON.
|  | Workflow Favourites | - Per-user star toggle on every workflow card - Stored under yourai_workflow_favourites_v1 (keyed by user id) - Top 4 surface in chat empty-state Favourites row - View all N → link - Hides when zero favourites | Complete | Favouriting a shared platform template doesn't mutate the shared record.
6.0 | Prompts & Templates | Prompt Templates Panel | - Full-page right-panel (showPromptPanel) - Template list: title + first 100 chars of prompt, category label, created date - Use button (pastes into input, focuses textarea) - Edit / Delete per template (with confirmation) - Create new template - Category filter tabs: All / Analysis / Review / Research / Summary / Drafting - Search by title + prompt text - Create/Edit modal: title, category dropdown, full prompt textarea - Empty state: 'No templates found.' | Complete | 5 default templates; user-created persist to yourai_prompt_templates_v1.
7.0 | Clients | Clients Panel | - Full-page right-panel (showClientsPanel) - Client list: name + contact + email + phone + type badge + last interaction - Contact / Edit / Delete actions - Search by name, contact, email; type filter dropdown - Add Client modal: name, contact, email, phone, type (Corporate/Individual/Government/Non-Profit), notes - Used as optional context in chat system prompt - Empty state: 'No clients found.' | Complete | yourai_clients_v1 localStorage. 3 default seed clients.
8.0 | Team & Workspace Management | Workspaces Selection | - Full-page /chat/workspaces route - Workspace card: name, description, team avatar stack, doc count, last updated - Click to enter workspace chat (/chat/workspaces/:id) - Create Workspace button - Search by name - Auto-routing: 0 → empty state · 1 → skip list · 2+ → list - Empty state: 'No workspaces found.' | Complete | External users land here by default.
|  | Workspace Chat (WorkspaceChatView) | - Same chat interface as main chat with workspace-scoped context - Workspace context banner: 'You are in [Workspace Name]' - Workspace-scoped documents (no personal vault access) - Workspace-scoped workflows - Real /api/chat execution (fixed 2026-04-25 — was on dead callLLM path) - Doc context inlined into user message - Source badge logic preserved | Complete | Has its own duplicate intent state. hasManualIntentPick pattern not yet audited here.
|  | Invite Team | - Full-page right-panel (showTeamPage) - Current team list: avatar, name, email, role, status (Active/Pending), Remove - Invite section: email input, role dropdown (Internal User / Client), Send Invites, Copy invite link - Activity log (recent invites/accepts/removals) - Sidebar member-count badge - Empty state: 'No team members yet.' | Complete | Visible to all non-External users (widened 2026-04-24). No real email delivery.
9.0 | Audit Logs (Tenant view) | Audit Logs Panel | - Full-page right-panel (showAuditLogsPanel) - Table: Timestamp / Action / User / Resource / Details - Filter by action type (Create/Edit/Delete/Share/Export/Run) - Filter by date range (Last 7d / 30d / This year / Custom) - Search by user or resource - Sort by date (newest first), user, action - Export to CSV (audit_log_[date].csv) - Pagination (>20 rows) | Planned | Mock data only — real audit logging not wired to /api/chat yet.
10.0 | Settings & Account | Sidebar Profile Menu | - Click avatar (top-right) opens dropdown - Current user name + email - Links: My Profile, Audit Logs (Org Admin), Billing (Org Admin), Settings - Sign out button (calls session.signOut, navigates to /chat/login) | Complete | Sidebar collapses on mobile.

## Super Admin
Super Admin
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | Dashboard & Overview | SA Dashboard | - Page header + subtitle - 6 StatCards: Total Orgs / Active / Suspended / MRR (gold) / Total Users / Active Users - Line chart: Revenue trend (last 12 months) - Pie chart: Plan breakdown (Free/Professional/Team/Enterprise) - Recent activity table (orgs created, users invited, billing changes) - Quick actions bar (Add Tenant / Add User / View Billing) | Complete | Mock data.
2.0 | Tenant Management | Tenant List | - 4 StatCards: Total / Active / Suspended / MRR - Filter bar: search by org name, plan dropdown (All/Free/Professional/Team/Enterprise), status dropdown (All/Active/Suspended) - Export CSV button (disabled when no results) - Showing N organisations label - Table: Organisation / Plan / Users / Workspaces / Documents / Status / Created / Actions - Per-row hover (ice-warm) - Action buttons: view (eye), edit, toggle suspend (Ban/CheckCircle) - Click row to open Org Detail slide-over - Add Tenant button (UserPlus icon, top-right) | Complete | yourai_mgmt_tenants localStorage mock. CSV export exports ALL not filtered. No suspend confirmation.
|  | Edit Tenant Modal | - Tenant name input - Plan dropdown - Status radio (Active / Suspended) - Suspend reason textarea (when suspending) - Billing info (read-only): MRR / Next renewal / Payment status - Save / Cancel / Delete | Complete
|  | Org Detail Slide-Over | - Right-docked 520px panel - Header: org name + status badge + close - Sections: Organization Info / Users / Workspaces / Documents / Billing - Action buttons: Edit / Suspend-Reactivate / Delete | Complete
|  | Add Tenant Slide-Over (3-step wizard) | - Step 1 — Organization Details: name, contact name, email, phone, website - Step 2 — Plan Selection: pricing cards with feature lists - Step 3 — Admin User: email, password, confirm password - Progress indicator (1/3, 2/3, 3/3) | Complete | Creates mock org + admin; no real Cognito wiring.
3.0 | User Management | Platform Users List | - 4 StatCards: Total / Active / Blocked / Invited (gold) - Search by name or email - Filters: Organisation dropdown / Role dropdown (All/Admin/Internal/Client) / Status dropdown - Export CSV button - Table: User / Email / Organisation / Role / Status / Last Active / Actions - Action buttons: Eye (view), Ban/CheckCircle (block/unblock) - Block hidden for Invited status | Complete | 10 hardcoded users in mock. No delete or edit user.
|  | User Detail Modal | - User avatar (56×56, navy, white initials) - Name + email + 2-col info grid (Organisation / Role / Status / Created / Last Active) - Activity Summary: Total Logins / Docs Uploaded - Onboarding Profile section (or 'not completed' card) - Block/Unblock button (red/green, hidden for Invited) | Complete
|  | Export CSV | - Filename: platform_users_export.csv - Header: Name,Email,Organisation,Role,Status,Last Active - Exports ALL users (not filtered) | Complete
4.0 | Knowledge Base — Legal Content | Legal Content Tab | - Tab bar: Legal Content (active) / Bot Persona / Alex Response Templates (disabled) - Info banner + 4 StatCards (Documents / Links / Total Size / Last Updated) - State Law Libraries section: Add State Library button, table (State / Assigned Documents / Status / Actions) - Manage State Library slide-over (520px): Assigned Documents list, Add More Documents checkbox list, Upload New Document - Add State Library modal: state dropdown + document checkbox list + Create Library - Document Upload area (2-col): file zone (drag-drop, PDF/DOCX/XLSX, 100MB max) + link zone (Add web link) - Search input - Documents table: File Name / Type / Size / Uploaded / Status / Delete (with inline confirm + 400ms fade) - Links table: Source Name / URL / Added / Status / Delete - Add Link modal: Source Name + URL inputs - Status pills: Indexing / Indexed / Failed / Active / Partial / Not Set | Complete | UI complete. No real crawling. Mock storage via localStorage.
5.0 | Knowledge Base — Bot Persona | Bot Persona Tab | - Info banner: 'What is Bot Persona?' - Status bar: 'Bot Persona Configuration' DM Serif heading + InfoButton tooltip + Active/Unsaved badge + version (vN, last saved by) + Read-only label - Per-intent card (12 ops): - - System prompt (read-only, gray bg) - - Tone prompt textarea (editable) - - Custom instruction textarea (editable, ≤500 chars) - - Keywords CSV list (editable) - - Opening behaviour dropdown (start_immediately / ask_for_document / ask_clarifying_question) - - Enabled toggle - - Save / Discard per card - Fallback chain explanation - Removed wireframe blocks (2026-04-26): Message Routing Flow + Per-Persona Response Format | In Progress | UI complete; only client-fallback callLLM reads it (Edge does NOT). Backend persistence is Phase 2 — see persona-dynamic-config-plan.md.
6.0 | Workflow Templates (Global) | Workflow Templates | - Template list with per-template card: name, description, practice area, step count, duration estimate, created by + date, status (Global/Org/Private) - View / Edit / Delete buttons - Create new template button - Filter tabs: All / Global / Featured - Search by name + description - Practice area filter dropdown - Detail view modal (read-only, all steps + prompts) | In Progress | Edit/delete not yet fully wired.
7.0 | Compliance & Notifications | Compliance Audit | - Audit results table: Framework / Status (Pass/Warning/Fail) / Last checked / Details - Generate audit report button - Audit history log | Planned | Placeholder UI; no real checks.
|  | Broadcast Notifications | - Notification list: title + message preview + audience + sent date - Compose modal: title, message textarea (markdown), audience dropdown, schedule (now/later), Send | Planned | Placeholder UI; no real delivery.
8.0 | Platform Settings | Platform Settings | - Email Configuration (SMTP, sender email) - API Keys Management - Feature Flags - Rate Limiting (requests/hour) - Data Retention Policy (days) - Backup Schedule (daily/weekly/monthly) | Planned | Placeholder mock UI.
|  | Platform Billing | - Revenue overview chart - Subscription breakdown (pie chart) - 4 StatCards: Active Subscriptions / MRR / LTV / Churn Rate - Invoice management table (org / plan / amount / date / status) - Invoice detail modal | Complete | Mock data.
|  | Usage Analytics | - Line chart: API calls over time - Bar chart: Usage by feature - Table: Usage by organisation - Date range picker - Export data button | Complete | Mock data.
|  | Integrations / FRD Generator / Bot Tester / User Stories | - /super-admin/integrations — placeholder list of connectors - /super-admin/frd-generator — POSTs to api/frd-generate.ts (separate Edge endpoint) - /super-admin/bot-tester — sandbox to fire prompts at the Edge with persona overrides - /super-admin/user-stories — 15 user-story screens listed in README | In Progress | FRD generator endpoint exists separately from /api/chat. Other surfaces are scaffolds.

## Org Admin
Org Admin
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | Dashboard | Org Dashboard | - Page header: 'Dashboard' + org name - 6 StatCards: Workspaces / Team Members / Documents Uploaded / Workflows Run / Active Users / Data Usage (GB) - Recent activity list (workspace created, user invited, doc uploaded, workflow run) - Quick action tiles: Create Workspace / Invite Team / Upload Documents / Run Workflow | Complete | Mock data.
2.0 | Workspace Management | Workspace List | - Create Workspace button (FolderPlus icon) - Search by workspace name - Sort dropdown (date, name, member count) - Workspace card grid (auto-fill, minmax 280px) — name, description, team avatar stack, doc count, last updated - Empty state: 'No workspaces yet.' - Breadcrumb: 'Dashboard > Workspaces' | Complete
|  | Workspace Detail | - Page header + breadcrumb (← Workspaces) - Tab bar: Overview / Documents / Members / Settings - Overview tab: name, description, created date, team avatars, recent docs (last 5), recent workflows (last 5) - Documents tab: workspace-scoped vault view - Members tab: per-member row (avatar, name, email, role, joined date), Remove + Invite + Role change - Settings tab: name input, description textarea, Privacy radio, Archive button, Delete (red, confirmation) - Action buttons: Classification modal / Generate Report / Run Workflow | Complete
3.0 | Document Management (Org-Level) | Org Document Vault | - Similar to chat vault but org-scoped - Org admin sees all org docs - Scope filter: All / My documents / Workspaces - Folder management at org level - Folder visibility radio (Private / Organization) - Bulk actions: delete multiple, move to folder, share - Advanced filters: owner, date, type, size - Audit trail per document | Complete | Some bulk features mock.
4.0 | Knowledge Packs (Org-Level) | Org Knowledge Packs | - Org admin sees all org packs - Create / edit / delete own packs - 'Make Global' button shares pack across org - Per-pack: owner, visibility (Private / Organization / Global) - Favorite toggle (per-user, separate) - Bulk actions: share, duplicate, export - Filter tabs: All / My Packs / Org / Global | Complete | Some actions mock.
5.0 | Workflows (Org-Level) | Org Workflows Page | - Header: 'AI Pipelines' - StatCards: Featured / Yours / Organization / Running - Tabs: Featured / Yours / Organization / All / Running - Search + practice-area filter - Card grid (similar to chat picker, org-specific) - Per-card: name, description, step count, owner, status (Draft/Active), Run, Star, Edit (owner/admin), Delete, View - Create new workflow → builder | Complete | Owner checks partly mock.
6.0 | Clients (Org-Level) | Org Clients | - Client list cards (name, contact, email, phone, type, last interaction) - Contact / Edit / Delete - Search + type filter + sort - Add Client modal - Empty state | Complete | Email/phone not real.
7.0 | User Management (Org-Level) | Org Users | - 4 StatCards: Total / Active / Pending Invites / Archived - Search + role filter + status filter - Invite User button (UserPlus) - Table: User / Email / Role / Status / Last Active / Actions (Eye/Edit/Remove) - Eye → user detail modal - Edit → role change dropdown - Remove → confirmation - Export CSV button - Invite modal: email (comma-separated) + role dropdown (Internal / Client) + Send + Copy link - User detail modal: info, activity (logins, docs uploaded, workflows run), Remove from org, Change role | Complete | Real invites mock.
8.0 | Billing & Usage (Org-Level) | Billing | - Current plan card: name, price, billing cycle, features, Upgrade/Downgrade/Renew - Invoice history table: number, date, amount, status, download - Payment method card: card type + last 4 + expiry + Update - Usage meter: workspace count, member count, storage GB - Upgrade modal: pricing cards (Professional / Team / Enterprise) | Complete | Real payment mock.
|  | Usage & Costs | - Line chart: API calls / storage over time - Cost breakdown table (feature / usage / unit cost / total) - Date range picker (7d / month / year / custom) - Export usage report (CSV) - Projected costs forecast | Complete | Mock data.
9.0 | Account & Profile | Profile Page | - Avatar upload - Name input (editable) + Email (read-only) - Professional Info: Role / Primary state / Firm size / Practice areas - Preferences (collapsible): email notifications toggles, Theme (Light/Dark/System), chat behavior, default workspace - Password Change: current / new (strength meter) / confirm - Two-Factor Auth (collapsible): toggle, backup codes, Add device - Save changes button + success/error toast | Complete | Password change not real.
|  | Organization Settings | - Org name input + logo upload + website + founded date - Admin Users list with Add Admin / Remove Admin (must keep ≥1) - Privacy & Data: data retention dropdown (30/90/365/indefinite), GDPR checkbox, Data export (JSON), Delete organization (red, password confirm) - Integrations: connected apps list (Slack, Teams), Connect new, Revoke access - Save changes button | Complete | Integrations mock.
|  | Org Audit Logs | - Org-scoped audit log table: Timestamp / Action / User / Resource / Details - Filter by action type, user, date range - Search by resource name - Export to CSV - Pagination | Complete | Mock data.
10.0 | Messages | Messages | - Conversation list (left sidebar): per-conv avatar, name, last-message preview, timestamp, unread badge, Search, Archive - Message thread (main): per-message avatar, name, body, timestamp, reactions (emoji), Reply, Delete (owner), Pin - Compose new message (search recipients) - Mark as read / unread | Planned | Placeholder; no real messaging backend.
11.0 | Reports | Reports | - Report type buttons: Activity / Usage / Workflows / Audit - Custom report builder: date range, metrics checkboxes, filters, chart type (line/bar/pie), Generate Report - Recent reports list (saved) - Export report (PDF / CSV / Excel) | Planned | Placeholder UI.

## Shared & Infra
Shared & Infra
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | API & Edge Functions | /api/chat — main LLM proxy | - Accepts {message, history, intent, system?} (UI shape) OR {messages: []} (workflow shape) - Injects per-intent JSON schema when intent is a card intent - Forces response_format: json_object on card intents - Streams SSE upstream → plain text/plain chunks downstream - Hardcoded 4-section system prompt: IN SCOPE / OUT OF SCOPE / MISSING DOCUMENT HANDLING / general accuracy - OpenAI gpt-4o-mini model, temp 0.7, max_tokens 2048 - 90s timeout via AbortController - Friendly error mapping (rate-limit, 401, context-length, model-not-found) - Response headers: X-Source-Type: AI_GENERATED | Complete | Edge function, runs on Vercel Edge runtime. process.env.OPENAI_API_KEY only.
|  | /api/frd-generate.ts | - Separate FRD generator endpoint - Used by /super-admin/frd-generator surface | In Progress | Complementary endpoint; not part of chat flow.
|  | Dead client-fallback (callLLM) | - src/lib/llm-client.ts — browser-side OpenAI call - Requires VITE_OPENAI_API_KEY (NEVER set in prod) - Reads SA-edited bot persona config (the only path that does) - Used to be the workflow / workspace chat / main chat path | Complete | DEAD in prod since 2026-04-25. File hangs on for hypothetical dev environments.
2.0 | Storage & Persistence | LocalStorage Keys | - yourai_auth_v1 — session token, user info - yourai_chat_history_v1 — message thread cache - yourai_document_vault_v2 — vault docs + folders (bumped 2026-04-27) - yourai_knowledge_packs_v1 — user KP list - yourai_workflows_v1 — workflow template definitions - yourai_workflow_runs_v1 — active + recent runs - yourai_workflow_favourites_v1 — per-user starred workflows - yourai_prompt_templates_v1 — user-created templates - yourai_clients_v1 — user-created client contacts - yourai_bot_persona — SA-edited persona config - yourai_sidebar_knowledge_open — sidebar collapse state - yourai_mgmt_users / yourai_mgmt_tenants — SA mock tables | Complete | All mock/client-side. Versioned for safe migration. No backend persistence yet.
|  | Sample seed PDFs (public/sample-docs/) | - MSA_Acme_Corp_v4.pdf - Employee_Handbook_2026.pdf - SeriesB_TermSheet_Signed.pdf - MSA_Acme_ScheduleA_SLAs.pdf (nested under Acme Corp / MSA & Schedules) - Generated by /tmp/gen-sample-pdfs.py from src/data/sampleVaultContent.ts (uses fpdf2) - Each DEFAULT_DOCUMENT_VAULT entry carries content + sampleUrl | Complete | Re-run generator when sample text changes. Vite copies public/ to dist/.
3.0 | Routing & Navigation | Route Structure | - Auth (no Layout): /chat/login /chat/signup /chat/forgot-password /chat/reset-password /chat/onboarding - Auth (SA): /super-admin/login /super-admin/verify-otp /super-admin/forgot-password /super-admin/reset-password - Tenant chat (ChatView + RoleProvider): /chat /chat/home /chat/workspaces /chat/workspaces/:id - Super Admin (Layout + ProtectedRoute): /super-admin/dashboard, /tenants, /users, /knowledge-base, /workflows, /billing, /usage, /compliance, /integrations, /notifications, /settings, /user-stories, /bot-tester, /frd-generator - Org Admin (OrgLayout + RoleProvider): /app/dashboard, /workspaces, /workspaces/:id, /vault, /knowledge-packs, /workflows, /clients, /users, /billing, /usage, /audit-logs, /profile, /settings, /messages, /prompt-templates, /reminders - Catch-all: / redirects to /super-admin/dashboard or /chat/home | Complete | React Router v6 BrowserRouter. ProtectedRoute + RoleContext for gating.
4.0 | Design System & Sub-Agents | CSS Design Tokens | - CSS variables: --navy, --gold, --green, --red, --ice-warm, --border, --text-secondary, --muted - Fonts: DM Serif Display (titles), DM Sans (body), IBM Plex Mono (mono — referenced but font not loaded; falls back to ui-monospace) - Lucide React icons (24-32px) - shadcn-ui Radix primitives (Dialog, Tooltip, Dropdown) - Tailwind utility classes (selective use alongside inline styles) | Complete | Tokens shipped; utilities ongoing.
|  | Sub-agents (.claude/agents/) | - aashna.md — senior UX designer persona (Linear/Stripe/Vercel background) - Output: diagnosis → prioritized fixes → paste-ready Claude Code implementation prompt - Used for layout / hierarchy / spacing audits | Complete | Used three times in 2026-04-24 session for Workflows / Builder / Run Panel rounds.
5.0 | Error Handling | Error Boundaries & Network Errors | - RouteErrorBoundary wraps workspace chat route - Generic error UI: 'Something went wrong. Please refresh.' - Chat error: 'AI service returned 503…' (real Edge error) - Timeout: 'AI service request timed out (90s)' - Network: 'Could not reach the AI service' - AbortError: silent (user-initiated cancel) - Errors shown as bot message in chat thread | Complete | Hardened 2026-04-25 (no more misleading 'No LLM backend available' fallback).
6.0 | Backlog (Wendy P-list & technical debt) | Wendy attorney feedback (P-list from 2026-04-27) | - P6 — Workspaces rename to 'Case Workspaces' (renamed then reverted; tile description softened to 'per-matter workspaces') - P9 — Default state-law KP per primary state (auto-attach) - P10 — Lexis / West integration over scraping (Karish to scope) - P11 — Default-open access within firm (flag flip pending) - P12 — Large-file (500-page PDF) strategy (auto-compression + per-case MD summary index) | Phase 2/3 | Captured in .claude-context/wendy-attorney-feedback.md. P1-P5, P7, P8.1, P8.2 already shipped.
|  | Vault Content Semantic Search (P8.4) | - PDF extraction → chunking → embedding → pgvector store - Hybrid retrieval: dense (pgvector kNN) + sparse (Postgres tsvector) + RRF merge - Cohere rerank-3 cross-encoder (top-50 → top-8) - LLM synthesis with citations [filename, p.N, §X] - Per-doc summary + two-pass retrieval (whole-doc questions on 500-page corpus) - Async ingestion job queue + status polling - ~3 weeks effort estimate; backend-dependent | Phase 2/3 | Full implementation guide in .claude-context/vault-content-rag-plan.md.
|  | SA Bot Persona dynamic config (backend wiring) | - intent_configs Postgres table (per-tenant, per-intent) - API: GET/PUT /api/intent-configs/:intentId - Wire tone + format_rules + custom_instruction into buildSystemPrompt() - Wire keywords into detectIntent() via ChatView - Wire opening_behaviour into ChatView pill selection - Wire requires_document gate into ChatView send - 6-8 days estimated effort | Phase 2/3 | Plan in .claude-context/persona-dynamic-config-plan.md.
|  | Technical debt | - Reconcile 3 sources of truth for intents (intents.ts / intentDetector.ts / GlobalKnowledgeBase.jsx DEFAULT_INTENTS) - Extend hasManualIntentPick pattern to WorkspaceChatView - YourVault content search (1-line change in filteredDocs to include d.content) - External-user single-workspace auto-redirect - Server-backed favourites (currently localStorage-only) - Server-side fix for JSON-schema-with-no-document failure mode at the Edge | Planned | Captured in PROGRESS.md 'What's next'.