## Overview
YourAI — Sprint 1 Feature Breakdown
Platform / Module Area | Total Modules | Total Sub-Modules | Total Features | Completion %
Sprint 1 — Tenant Chat | 8 | 22 | 70 | 93.18%
Grand Total | 8 | 22 | 70 | 93.18%
Status legend
Complete | Fully implemented and live in production (UI + flow).
In Progress | Surface complete; backend persistence or polish pending.
Planned | Scope agreed; not yet started this sprint.
Phase 2/3 | Out of Sprint 1 scope; tracked for later phases.

## Sprint 1 — Features
Sprint 1 — Features
Sr. No. | Modules | Sub-Modules | Features / WBS | Status | Notes / Remarks
1.0 | Chat | Conversation | - Send a message and receive a streamed AI response - Source attribution on each answer (document, vault, or knowledge pack) - Start a fresh conversation at any time - Friendly empty state with suggested prompts to get started | Complete | Tenant landing surface for non-external users.
|  | History & search | - Recent threads list in the sidebar - Search across past conversations by keyword (titles + bodies) - Snippet preview on body matches | In Progress | UI complete; backend persistence of threads pending.
|  | Trust signals | - Disclaimer below the input ('may produce inaccurate information') - Private & encrypted indicator | Complete
2.0 | Document Upload | Attach to chat | - Attach files via the + button on the chat input - Drag-and-drop files anywhere on the chat surface - Persistent drop zone (stays visible throughout the conversation) - Per-file remove chip before sending | Complete
|  | Multi-file upload | - Upload multiple documents in a single action - Cap of 10 files per upload - Mixed file types in one action (PDF, DOCX, TXT) | Complete | Limit configurable; current cap = 10.
|  | Auto-save to vault | - Uploaded files auto-save into YourVault on attach - Extracted text saved alongside metadata so the doc is searchable later | In Progress | UI complete; backend persistence in flight.
3.0 | Attach Document from YourVault | Vault picker | - Open the picker from the + button on the chat input - Search the vault by document name in real time - Folder breadcrumb shown alongside each result | Complete
|  | Attach / detach | - One-click attach a vault document to the current chat - Detach the attached vault document mid-thread - 'Open YourVault →' shortcut to the full library | Complete
4.0 | Knowledge Pack | Browse & manage | - Browse all knowledge packs the user has access to - Create a new knowledge pack (name, description, scope) - Edit and delete a pack - Add documents and links to a pack | In Progress | UI complete; backend persistence in flight.
|  | Visibility | - Share a pack org-wide - Keep a pack private to the creator | Complete
|  | Use in chat | - Attach a knowledge pack to a chat from the chat input - Switch the active pack mid-conversation - Active pack visible in the chat header/breadcrumb - 'Manage knowledge packs →' shortcut from the chat input | Complete
5.0 | Adding Documents Mid-Conversation | Additive uploads | - Upload an additional document at any point in an active chat - Each new document labelled in conversation ('Document 2 — added 3:42 PM') - AI disambiguates between original and added documents when answering - All attached documents remain visible and removable | Complete | Replaces the prior 'one upload per chat' rule (Wendy interview, Apr 27).
|  | New-thread escape hatch | - Inline cue: 'New topic? Start a fresh chat →' after each additive upload - One-click starts a new thread without leaving the page | Complete
6.0 | Chit-Chat Handling | Casual conversation | - Bot replies warmly to greetings ('hi', 'hey', 'thanks') - Casual messages do not trigger document-analysis output - 'What can you do?' returns a short capability summary | Complete | Even when a task like Risk Memo is selected.
|  | Smart guidance | - Bot reminds user of the active task and what to upload (when relevant) - Works whether or not a task is selected - Works whether or not a document is attached | Complete
7.0 | Tasks (Intents) & Auto-Switch | Pick a task | - Pick a task from a dropdown (Summary / Compare / Risk Memo / Case Brief / Research / Clauses / Timeline / Find Document / General Chat) - Tasks grouped by category (Ask & Research / Analyze / Draft) - Selected task visible above the input | Complete
|  | Auto-detect & switch | - Auto-detect the task from the user's first message ('review this contract' → Risk Memo) - Silent switch with a small 'Switched to X mode' note in the conversation - Manual pick always wins over auto-detection - Suggestion banner when more than one task could match the message | Complete | Forceful auto-switch is the default; user override is sticky.
|  | Mid-thread change | - Change the task at any point in the conversation - Conversation history is preserved across the switch - No 'start fresh conversation' interrupt | Complete
|  | Doc-source confirmation | - Confirmation prompt before running an analysis on already-attached documents - User can confirm with 'Yes, use it' or upload a new document instead | Complete | Rendered as plain prose with text links (PM call: not a styled card).
8.0 | Task Outputs (Reports) | Card-type reports | - Risk Memo - Document Summary - Comparison - Case Brief - Legal Research - Clause Analysis - Timeline | Complete | 7 card types in Sprint 1.
|  | Side-panel reading | - Reports open in a clean side-panel report view (reads like a memo, not a UI dashboard) - Fullscreen mode for reading long reports - Copy report as Markdown for pasting into Word, Notion, or email | Complete | Claude-style artifact panel; right-rail.
|  | Empty state | - Friendly upload prompt when no document is attached - Hint pointing to a sibling task ('try Clause Analysis instead') | Complete